## Slide 1: EXERCISE PROCESS (HSEEP)

## Slide 2: EXERCISE PROCESS (HSEEP)
BECOME FAMILAR WITH YOUR AGENCY, COUNTY OR DEPARTMENT- REVIEW ALL EOP, SOP & PAST EXPERIENCE AND EXERCISES IF DEVELOPED
CONDUCT HAZARD ANALYISIS- IDENTIFY THREATS AND HAZARDS TO YOUR COMMUNITY OR ORANIZATION
DETERMINE WHICH THREATS OR HAZARDS WILL HAVE THE MOST IMACT ON YOUR COMMUNITY OR ORGANIZATION- PRIORITIZE THREATS AND HAZARDS

## Slide 3: EXERCISE PROCESS (HSEEP)
DEVELOP OR UPDATE EMERGENCY RESPONSE PLANS, EOP, POLICES AND PROCEDURES TO ADDRESS THESE THREATS AND HAZARDS
PURCHASE, OBTAIN OR IDENTIFY RESOURCES OR EQUIPMENT NEEDED TO PREPARE AND RESPOND TO THREAT OR HAZARD
DEVELOP TRAINNG AND EXERCIES (TEPW) BASED ON YOUR EOP, SOP OR POLICES AND PROCEDURES WHICH WILL BE TARGETED TOWARD THE MOST SIGNIFICANT THREAT OR HAZARD

## Slide 4: EXERCISE PROCESS (HSEEP)
ONCE TRAINING OF YOUR EOP, POLICY OR SOP COMPLETE, BEGIN PROCESS TO TEST THOSE PLANS
CHOOSE EXERCISE DIRECTOR AND YOUR PLANNING TEAM TO DESIGN EXERCISE
CONDUCT CONCEPT AND OBJECTIVES MEETING (C/O) OR INITIAL PLANNING MEETING (MAY BE COMBINED)

## Slide 5: EXERCISE PROCESS (HSEEP)
EXERCISE TEAM WILL LOOK AT CAPABILITES FROM CORE CAPABILITY LIST AND CHOOSE WHICH CAPABILITIES YOU WANT TO ADDRESS AND TEST
DETERMINE OBJECTIVES OF EXERCISE
OF THE CAPABILITIES CHOSEN (EEG), CHOOSE OR DEVELOP THE ACTIVITIES OR TASKS YOUR TEAM WANTS TO TEST (DISCUSSION OR ACTIONS YOU WANT TO SEE OCCUR IN EXERCISE) BASED OFF OF YOUR EOP, SOP, POLICY OR PROCEDURE

## Slide 6: EXERCISE PROCESS (HSEEP)
DETERMINE MEETING/EXERCISE SCHEDULE (IPM, MPM, MSEL, FPM)
DESIGN EXERCISE SCENARIO- SHOULD FIT OBJECTIVES & BASED ON REAL THREAT
ASSIGN WORK (PLANNING SECTION =SITUATION MANUAL, EXERCISE PLAN, CONTROLLER & EVALUATOR HANDBOOK, MSEL), (LOGISTICS= ALL RESOURCES NEEDED)

## Slide 7: EXERCISE PROCESS (HSEEP)
CONTINUE MEETINGS (MPM, MSEL, FPM)
EXERCISE DIRECTOR OVERSEES ALL PROGRESS
PRIOR TO THE EXERCISE, CONDUCT BRIEFS (CONTROLLER, EVALUATOR, ACTOR, OBSERVER, HOSPITAL AND MEDIA)

## Slide 8: EXERCISE PROCESS (HSEEP)
CONDUCT AND EVALUATE EXERCISE
HOT WASH/ANALYZE EXERCISE
DEVELOP AAR/IP (AAR MEETING)

## Slide 9: EXERCISE PROCESS (HSEEP)
FOLLOW UP THE IP- MAKE SURE IMPROVEMENTS ARE IMPLEMENTED
THEN TEST THE SAME THREAT/HAZARD AT THE NEXT LEVEL (TABLETOP TO FUNCTIONAL TO FULL SCALE)
CHOOSE EXERCISE DIRECTOR AND PLANNING TEAM